## SBC04_VoLTE LI
Case No | Type | Scenarios
|  |  | Status | Tested On | Tested On | Duration | Target Number | Fanout Number | Multiple fanout | A-Party | B-Party | C-Party | CRI VALIDATION | MEDIATION SERVER IP | MEDIATION SERVER HOST NAME | Zeel reamark
|  |  |  | (Date ) | (Time)
LI_1 | MSISDN | Regular Voice Call_MO (VoLTE)from Handset | OK | 2026-06-22 | 17:09 | 1:00 | 9916349635 | 9986206416 |  | 9916349635 | 9743278355
LI_2 | MSISDN | Regular Voice Call_MO (VoLTE)from Apple I watch | I watch not available |  |  |  | 9986294061
LI_3 | MSISDN | Regular Voice Call_MT (VoLTE) received on Handset | OK | 2026-06-22 | 17:17 | 1:00 | 9916349635 | 9986206416 |  | 9743278355 | 9916349635
LI_4 | MSISDN | Regular Voice Call_MT (VoLTE) received on I watch | I watch not available |  |  |  | 9986294061
LI_5 | MSISDN | Regular Voice Call_MO (Breakout) from Handset | OK | 2026-06-22 | 17:18 | 1:00 | 9916349635 | 9986206416 |  | 9916349635 | 9689311089
LI_6 | MSISDN | Regular Voice Call_MO (Breakout) from I watch | I watch not available |  |  |  | 9986294061
LI_7 | MSISDN | Regular Voice Call_MT (Breakin)received on Handset | OK | 2026-06-22 | 17:20 | 1:00 | 9916349635 | 9986206416 |  | 9689311089 | 9916349635
LI_8 | MSISDN | Regular Voice Call_MT (Breakin)received on I watch | I watch not available |  |  |  | 9986294061
LI_9 | MSISDN | Regular SMS _MO (Breakout) | OK | 2026-06-22 | 17:24 |  | 9916349635 | 9986206416 |  | 9916349635 | 9689311089
LI_10 | MSISDN | Regular SMS _MT (Brwakin) | NOK |  |  |  | 9916349635 | 9986206416 |  | 9689311089 | 9916349635
LI_11 | MSISDN | Regular SMS _MO (VoLTE) | OK | 2026-06-22 | 17:26 |  | 9916349635 | 9986206416 |  | 9916349635 | 9743278355
LI_12 | MSISDN | Regular SMS _MT (VoLTE) | NOK |  |  |  | 9916349635 | 9986206416 |  |  | 9916349635
LI_13 | MSISDN | MO/MO Conf. | OK | 2026-06-22 | 18:12 | 1:00 | 9916349635 | 9986206416 |  | 9916349635 | 9620902766 | 9689311089
LI_14 | MSISDN | MT/MT Conf | OK | 2026-06-22 | 18:16 | 1:00 | 9916349635 | 9986206416 |  | 9620902766 | 9916349635 | 9689311089
LI_15 | MSISDN | Voice Call Forwarding (not reachable) B Forwarded to C | OK | 2026-06-22 | 17:36 | 1:00 | 9916349635 | 9986206416 |  | 9743278355 | 9916349635 | 9689311089
LI_16 | MSISDN | Voice Call Forwarding (no reply) B Forwarded to C | OK | 2026-06-22 | 17:39 | 1:00 | 9916349635 | 9986206416 |  | 9743278355 | 9916349635 | 9689311089
LI_17 | MSISDN | Voice Call Forwarding (Unconditional) B Forwarded to C | OK | 2026-06-22 | 17:43 | 1:00 | 9916349635 | 9986206416 |  | 9743278355 | 9916349635 | 9689311089
LI_18 | MSISDN | Voice Call Forwarding (user busy) B Forwarded to C | OK | 2026-06-22 | 17:41 | 1:00 | 9916349635 | 9986206416 |  | 9743278355 | 9916349635 | 9689311089
LI_19 | MSISDN | Voice to Video Switch over | OK | 2026-06-22 | 18:05 | 1:00 | 9916349635 | 9986206416 |  | 9916349635 | 9620902766
LI_20 | MSISDN | Video to Voice Switch over | OK | 2026-06-22 | 18:07 | 1:00 | 9916349635 | 9986206416 |  | 9916349635 | 9620902766
LI_21 | MSISDN | USSD Interception | OK | 2026-06-22 | 18:09 |  | 9916349635 | 9986206416 |  | 9916349635 | *199#
LI_22 | MSISDN | DTMF | OK | 2026-06-22 | 18:10 | 1:00 | 9916349635 | 9986206416 |  | 9916349635 | 9620902766 | [5 empty] | 12345 | 54321
LI_23 | MSISDN | Multiple Fan out Voice (MO) | WIP |  |  | 1:00 | 9916349635 | 9986206416 |  | 9916349635 | 9620902766
LI_24 | MSISDN | Multiple Fan out Voice (MT) | WIP |  |  | 1:00 | 9916349635 | 9986206416
LI_25 | MSISDN | Multiple Fan out Video (MO) | WIP |  |  | 1:00 | 9916349635 | 9986206416
LI_26 | MSISDN | Multiple Fan out Video (MT) | WIP |  |  | 1:00 | 9916349635 | 9986206416
LI_27 | MSISDN | Multiple Fan out Video (Voice to Video) | WIP |  |  | 1:00 | 9916349635 | 9986206416
LI_28 | MSISDN | Multiple Fan out Video (Video to Voice) | WIP |  |  | 1:00 | 9916349635 | 9986206416
LI_29 | IMSI | Regular Voice Call_MO (VoLTE)
LI_30 | IMSI | Regular Voice Call_MT (VoLTE)
LI_31 | IMSI | Regular Voice Call_MO (Breakout)
LI_32 | IMSI | Regular Voice Call_MT (Breakin)
LI_33 | IMEI | Regular Voice Call_MO (VoLTE)
LI_34 | IMEI | Regular Voice Call_MT (VoLTE)
LI_35 | IMEI | Regular Voice Call_MO (Breakout)
LI_36 | IMEI | Regular Voice Call_MT (Breakin)
THE FOLLOWING TEST CASES MUST BE PERFORMED ON THE REMAINING MEDIATION SERVERS
Case No | Type | Scenarios
|  |  | Status | Tested On | Tested On | Duration | Target Number | Fanout Number | Multiple fanout | A-Party | B-Party | C-Party | CRI VALIDATION | MEDIATION SERVER IP | MEDIATION SERVER HOST NAME
|  |  |  | (Date ) | (Time)
LI_1 | MSISDN | Regular Voice Call_MO (VoLTE)
LI_2 | MSISDN | Regular Voice Call_MT (VoLTE)
LI_3 | MSISDN | Regular Voice Call_MO (Breakout)
LI_4 | IMSI | Regular Voice Call_MT (Breakin)
Case No | Type | Scenarios
|  |  | Status | Tested On | Tested On | Duration | Target Number | Fanout Number | Multiple fanout | A-Party | B-Party | C-Party | CRI VALIDATION | MEDIATION SERVER IP | MEDIATION SERVER HOST NAME
|  |  |  | (Date ) | (Time)
LI_1 | MSISDN | Regular Voice Call_MO (VoLTE)
LI_2 | MSISDN | Regular Voice Call_MT (VoLTE)
LI_3 | MSISDN | Regular Voice Call_MO (Breakout)
LI_4 | IMSI | Regular Voice Call_MT (Breakin)
| SR.NO. | Following artefacts to be captured and attach in the next sheets |  |  | Captured Status ( YES/NO)
| 1 | Attach X1/X2/X3 ping & traceroutes between peer nodes (Forwards & Reverse)
| 2 | Route snapshot from Mediation servers
| 3 | Routing table dump from all mediation servers

## Summary
| SBC04 | Completed | SBC05 | Completed | SBC06 | Completed
MSISDN | 28 | 20 | 28 |  | 28
IMSI | 4 |  | 4 |  | 4
IMEI | 4 |  | 4 |  | 4
Total | 36 | 20 | 36 | 0 | 36 | 0

## Sheet1
Target Number | Target Type | Number belongs to | Interception Circle | Number Type | Test Period | Fan Out No | Purpose
9916349635 | MSISDN | KAR VF | Karnataka | Test | 18-06-2026 to 18-07-2026 | 041218722830612-KARTST MUID | BTP New IMS setup testing
041219986206416-KARTST1 MUID
404446911249920 | IMSI | KAR IDEA | Karnataka | Test | 18-06-2026 to 18-07-2026 | 041218722830612-KARTST MUID | BTP New IMS setup testing
[6 empty] | 041219986206416-KARTST1 MUID |  | SBC06
9620575949 | MSISDN | KAR VF | Karnataka | Test | 18-06-2026 to 18-07-2026 | 041218722830612-KARTST MUID | BTP New IMS setup testing
041219986206416-KARTST1 MUID
404446911249954 | IMSI | KAR IDEA | Karnataka | Test | 18-06-2026 to 18-07-2026 | 041218722830612-KARTST MUID | BTP New IMS setup testing
041219986206416-KARTST1 MUID
9916899497 | MSISDN | KAR VF | Karnataka | Test | 18-06-2026 to 18-07-2026 | 041218722830612-KARTST MUID | BTP New IMS setup testing
041219986206416-KARTST1 MUID
404446911250190 | IMSI | KAR IDEA | Karnataka | Test | 18-06-2026 to 18-07-2026 | 041218722830612-KARTST MUID | BTP New IMS setup testing
041219986206416-KARTST1 MUID
382822574888054 | IMEI |  | Karnataka | Test | 18-06-2026 to 18-07-2026 | 041218722830612-KARTST MUID | BTP New IMS setup testing
35354242-488805-0
8722385392 Idea prepaid 404446911250190 SBC06+CFX02+TAS03
9743278355 Idea_Postpaid 404446910557966 SBC05+CFX03+TAS04
9743560402 Idea_Postpaid 404446910557968 SBC04+CFX02+TAS03
9620902766 | VF_Postpaid | 404860430553829 | SBC05+CFX02+TAS03

## SBC06_VoLTE LI
Case No | Type | Scenarios
|  |  | Status | Tested On | Tested On | Duration | Target Number | Fanout Number | Multiple fanout | A-Party | B-Party | C-Party | CRI VALIDATION | MEDIATION SERVER IP | MEDIATION SERVER HOST NAME | Zeel reamark
|  |  |  | (Date ) | (Time)
LI_1 | MSISDN | Regular Voice Call_MO (VoLTE)from Handset | OK | 2026-06-23 | 16:15 | 1:00 | 9916899497 | 9986206416 |  | 9916899497 | 9743278355
LI_2 | MSISDN | Regular Voice Call_MO (VoLTE)from Apple I watch | I watch not available |  |  |  | 9620575949 | 9986206416
LI_3 | MSISDN | Regular Voice Call_MT (VoLTE) received on Handset | OK | 2026-06-23 | 16:25 | 1:00 | 9916899497 | 9986206416 |  | 9743278355 | 9916899497
LI_4 | MSISDN | Regular Voice Call_MT (VoLTE) received on I watch | I watch not available |  |  |  | 9620575949 | 9986206416
LI_5 | MSISDN | Regular Voice Call_MO (Breakout) from Handset | OK | 2026-06-23 | 16:21 | 1:00 | 9916899497 | 9986206416 |  | 9916899497 | 9689311089
LI_6 | MSISDN | Regular Voice Call_MO (Breakout) from I watch | I watch not available |  |  |  | 9620575949 | 9986206416
LI_7 | MSISDN | Regular Voice Call_MT (Breakin)received on Handset | OK | 2026-06-23 | 16:19 | 1:00 | 9916899497 | 9986206416 |  | 9689311089 | 9916899497
LI_8 | MSISDN | Regular Voice Call_MT (Breakin)received on I watch | I watch not available |  |  |  | 9620575949 | 9986206416
LI_9 | MSISDN | Regular SMS _MO (Breakout) |  | 2026-06-23 |  |  | 9916899497 | 9986206416 |  | 9916899497 | 9689311089
LI_10 | MSISDN | Regular SMS _MT (Brwakin) |  | 2026-06-23 |  |  | 9916899497 | 9986206416 |  | 9689311089 | 9916899497
LI_11 | MSISDN | Regular SMS _MO (VoLTE) |  | 2026-06-23 |  |  | 9916899497 | 9986206416
LI_12 | MSISDN | Regular SMS _MT (VoLTE) |  | 2026-06-23 |  |  | 9916899497 | 9986206416
LI_13 | MSISDN | MO/MO Conf. |  | 2026-06-23 |  | 1:00 | 9916899497 | 9986206416
LI_14 | MSISDN | MT/MT Conf |  | 2026-06-23 |  | 1:00 | 9916899497 | 9986206416
LI_15 | MSISDN | Voice Call Forwarding (not reachable) B Forwarded to C |  | 2026-06-23 |  | 1:00 | 9916899497 | 9986206416
LI_16 | MSISDN | Voice Call Forwarding (no reply) B Forwarded to C |  | 2026-06-23 |  | 1:00 | 9916899497 | 9986206416
LI_17 | MSISDN | Voice Call Forwarding (Unconditional) B Forwarded to C |  | 2026-06-23 |  | 1:00 | 9916899497 | 9986206416
LI_18 | MSISDN | Voice Call Forwarding (user busy) B Forwarded to C |  | 2026-06-23 |  | 1:00 | 9916899497 | 9986206416
LI_19 | MSISDN | Voice to Video Switch over | OK | 2026-06-23 | 16:28 | 1:00 | 9916899497 | 9986206416 |  | 9916899497 | 9743278355
LI_20 | MSISDN | Video to Voice Switch over | OK | 2026-06-23 | 16:29 | 1:00 | 9916899497 | 9986206416 |  | 9916899497 | 9743278355
LI_21 | MSISDN | USSD Interception |  | 2026-06-23 |  | 1:00 | 9916899497 | 9986206416 |  | 9916899497
LI_22 | MSISDN | DTMF |  | 2026-06-23 |  | 1:00 | 9916899497 | 9986206416 |  | 9916899497 | 9743278355 | [5 empty] | 1234567 | 7654321
LI_23 | MSISDN | Multiple Fan out Voice (MO) |  | 2026-06-23 |  | 1:00 | 9916899497 | 9986206416
LI_24 | MSISDN | Multiple Fan out Voice (MT) |  | 2026-06-23 |  | 1:00 | 9916899497 | 9986206416
LI_25 | MSISDN | Multiple Fan out Video (MO) |  | 2026-06-23 |  | 1:00 | 9916899497 | 9986206416
LI_26 | MSISDN | Multiple Fan out Video (MT) |  | 2026-06-23 |  | 1:00 | 9916899497 | 9986206416
LI_27 | MSISDN | Multiple Fan out Video (Voice to Video) |  | 2026-06-23 |  | 1:00 | 9916899497 | 9986206416
LI_28 | MSISDN | Multiple Fan out Video (Video to Voice) |  | 2026-06-23 |  | 1:00 | 9916899497 | 9986206416
LI_29 | IMSI | Regular Voice Call_MO (VoLTE)
LI_30 | IMSI | Regular Voice Call_MT (VoLTE)
LI_31 | IMSI | Regular Voice Call_MO (Breakout)
LI_32 | IMSI | Regular Voice Call_MT (Breakin)
LI_33 | IMEI | Regular Voice Call_MO (VoLTE)
LI_34 | IMEI | Regular Voice Call_MT (VoLTE)
LI_35 | IMEI | Regular Voice Call_MO (Breakout)
LI_36 | IMEI | Regular Voice Call_MT (Breakin)
THE FOLLOWING TEST CASES MUST BE PERFORMED ON THE REMAINING MEDIATION SERVERS
Case No | Type | Scenarios
|  |  | Status | Tested On | Tested On | Duration | Target Number | Fanout Number | Multiple fanout | A-Party | B-Party | C-Party | CRI VALIDATION | MEDIATION SERVER IP | MEDIATION SERVER HOST NAME
|  |  |  | (Date ) | (Time)
LI_1 | MSISDN | Regular Voice Call_MO (VoLTE)
LI_2 | MSISDN | Regular Voice Call_MT (VoLTE)
LI_3 | MSISDN | Regular Voice Call_MO (Breakout)
LI_4 | IMSI | Regular Voice Call_MT (Breakin)
Case No | Type | Scenarios
|  |  | Status | Tested On | Tested On | Duration | Target Number | Fanout Number | Multiple fanout | A-Party | B-Party | C-Party | CRI VALIDATION | MEDIATION SERVER IP | MEDIATION SERVER HOST NAME
|  |  |  | (Date ) | (Time)
LI_1 | MSISDN | Regular Voice Call_MO (VoLTE)
LI_2 | MSISDN | Regular Voice Call_MT (VoLTE)
LI_3 | MSISDN | Regular Voice Call_MO (Breakout)
LI_4 | IMSI | Regular Voice Call_MT (Breakin)
| SR.NO. | Following artefacts to be captured and attach in the next sheets |  |  | Captured Status ( YES/NO)
| 1 | Attach X1/X2/X3 ping & traceroutes between peer nodes (Forwards & Reverse)
| 2 | Route snapshot from Mediation servers
| 3 | Routing table dump from all mediation servers