## Summary-KAR-SBC06
Test Cases | Scope | Completed Cases | % Completion | Pending Cases | Dependency & Support required
Audio Conference | 1 | 0 | 0% | 1
Basic Calls & Announcements | 10 | 0 | 0% | 10
Billing-Postpaid | 4 | 0 | 0% | 4
Dialing Pattern | 2 | 0 | 0% | 2
Emergency Services | 1 | 0 | 0% | 1
Functional Test Cases | 7 | 0 | 0% | 7
Lawful Interception | 8 | 0 | 0% | 8
Registration | 4 | 0 | 0% | 4
Roaming | 2 | 0 | 0% | 2 | Post cutover 10k
SRVCC | 2 | 0 | 0% | 2 | Need Circle Support
VAS Services | 1 | 0 | 0% | 1
PLMN Wise testing-IDEA | 12 | 0 | 0% | 12
Grand Total | 54 | 0 | 0% | 54

## KAR-SBC06
Category | TC ID | Test Cases | Status | A Number | B Number | C Number | Remark
Basic Calls & Announcements | BCA_1 | VoLTE to VoLTE A Clear | OK | 9986205978 | 8722385392
Basic Calls & Announcements | BCA_8 | VoLTE to VoLTE -B Put on Hold & Then Resume | OK | 9986205978 | 8722385392
Basic Calls & Announcements | BCA_11 | VoLTE to 2G/3G B Clear | OK | 9986205978 | 8722385392
Basic Calls & Announcements | BCA_17 | VoLTE to 2G/3G -B Put on Hold & Then Resume | OK | 9986205978 | 8722385392
Basic Calls & Announcements | BCA_107 | VoLTE to 2G/3G(Other operator) A Clear | OK | 9986205978 | 9939200669
Basic Calls & Announcements | BCA_116 | VoLTE to 2G/3G(Other operator) -B is on another call | OK | 9986205978 | 9939200669
Basic Calls & Announcements | BCA_19 | 2G/3G to VoLTE A Clear | OK | 8722385392 | 9986205978
Basic Calls & Announcements | BCA_30 | VoLTE (in 2G/3G) to VoLTE B Clear | OK | 8722385392 | 9986205978
Basic Calls & Announcements | BCA_118 | 2G/3G (Other Operator) to VoLTE A Clear | OK | 9939200669 | 9986205978
Basic Calls & Announcements | BCA_97 | Video:VoLTE to VoLTE A Clear | OK | 8722385392 | 9986205978
Registration | Reg_1 | SIP Registration IMS AKA (IMS Registeration) | OK | 9986205978
Registration | Reg_3 | UE Registration (SUBSCRIBE/NOTIFY dialog included). | OK | 9986205978
Registration | Reg_4 | UE initiated De-Registration (SUBSCRIBE/NOTIFY dialog included). | OK | 9986205978
Registration | Reg_5 | UE Refresh-Registration. | OK | 9986205978
Dialing Pattern | DLP8 | Customer Care: 9092012345/9092000198 | OK | 9986205978
Dialing Pattern | DLP11 | NTFS: 18602102484 | NOK | 9986205978
Emergency Services | ES6 | Check Emergency Service with all Emergency Numbers (100/101-----112) | OK | 9986205978
Functional Test Cases | FNC_21 | Short Message using IPSMGW, VoTLE to VoLTE | OK | 9986205978 | 8722385392
Audio Conference | MPTY2 | To Verify the Conference Calling when 3 participants are VoLTE in VoLTE Coverage and 2 participants are in CS coverage. |  | 9986205978 | 8722385392 | 9620902766 | 3-handset are using
VAS Services | VAS_27 | Short Codes: 198
Functional Test Cases | FNC_10 | Audio to Video Upgrade
Functional Test Cases | FNC_11 | Video to Audio downgrade
Functional Test Cases | FNC_12 | Video Call Hold & Resume
Functional Test Cases | FNC_13 | VoWifi to VoWifi, A clears
Functional Test Cases | FNC_14 | VoWifi to Volte, B clears
Functional Test Cases | FNC_15 | VoLTE to VoWIFI, B clears
SRVCC | eSRVCC_1 | To verify that calling party VoLTE (A) is able to make eSRVCC handover to 3G/2G during active call | circle support required
SRVCC | eSRVCC_2 | To verify that called party VoLTE (B) is able to make eSRVCC handover to 3G/2G during active call | circle support required
Billing-Postpaid | Interbrand | VoLTE (e-VF PLMN x ) subscriber making call to VoLTE (e-Idea PLMN x) subscriber, Home PLMN
Billing-Postpaid | Interbrand | VoLTE (eIdea, PLMN x) subscriber making call to VoLTE (e-VF, PLMN x) subscriber, Home PLMN
Billing-Postpaid | Interbrand | VoLTE (e-VF PLMN x ) subscriber making call to VoLTE (e-Idea PLMN y) subscriber, Inter PLMN
Billing-Postpaid | Interbrand | VoLTE (eIdea, PLMN x) subscriber making call to VoLTE (e-VF, PLMN y) subscriber, Inter PLMN
Roaming | ROAM1 | Verify Roaming User is able to Register from Visiting Circle. | OK |  |  |  | Post cutover 10k
Roaming | ROAM2 | Roaming User Outgoing/Incoming Voice Call to Volte and CS network | OK |  |  |  | Post cutover 10k
Lawful Interception | LI_MSISDN_1 | Regular Voice Call_MO (VoLTE)
Lawful Interception | LI_MSISDN_2 | Regular Voice Call_MT (VoLTE)
Lawful Interception | LI_MSISDN_3 | Regular Voice Call_MO (Breakout)
Lawful Interception | LI_MSISDN_4 | Regular Voice Call_MT (Breakin)
Lawful Interception | LI_IMSI_1 | Regular Voice Call_MO (VoLTE)
Lawful Interception | LI_IMSI_2 | Regular Voice Call_MT (VoLTE)
Lawful Interception | LI_IMSI_3 | Regular Voice Call_MO (Breakout)
Lawful Interception | LI_IMSI_4 | Regular Voice Call_MT (Breakin)
PLMN Wise testing | PLMN_1-IDEA | Registration PLMN-2 (IDEA MAG)
PLMN Wise testing | PLMN_10-IDEA | Short Message - CS to VoLTE (to IDEA MAG)
PLMN Wise testing | PLMN_11-IDEA | Video call MO-from IDEA MAG
PLMN Wise testing | PLMN_12-IDEA | Video call MT-to IDEA MAG
PLMN Wise testing | PLMN_13-IDEA | Call Forwarding Unconditional. (With Notification to A party) to IDEA MAG VoLTE
PLMN Wise testing | PLMN_2-IDEA | VoLTE to VoLTE A Clear (IDEA MAG to IDEA MAG)
PLMN Wise testing | PLMN_3-IDEA | VoLTE to VoLTE A Clear (IDEA MAG to MAG-VF)
PLMN Wise testing | PLMN_4-IDEA | VoLTE to VoLTE A Clear (MAG-VF to IDEA MAG)
PLMN Wise testing | PLMN_6-IDEA | VoLTE to 2G/3G(Other operator) B Clear from IDEA MAG
PLMN Wise testing | PLMN_7-IDEA | 2G/3G to VoLTE B Clear (to MAG IDEA)
PLMN Wise testing | PLMN_8-IDEA | Short Message - VoLTE to CS(from IDEA MAG)
PLMN Wise testing | PLMN_9-IDEA | Short Message - VOLTE to VoLTE (from IDEA MAG)

## Sheet1 (hidden)
SNO. | Circle | MSISDN | IMSI | Brand | Pre /Postpaid |  | SBC | Dummy Zone | Live Zone
1 | Raj | 9672005028 | 404604770207760 | Vodafone | Postpaid | LI | SBC05 | ims.mnc060.mcc105.3gppnetwork.org | ims.mnc060.mcc404 | OK | OK
2 | Raj | 9672005034 | 404604770207762 | Vodafone | Postpaid | LI | SBC05 | ims.mnc060.mcc105.3gppnetwork.org | ims.mnc060.mcc404 |  | OK
3 | Raj | 8094199250 | 404604770207800 | Vodafone | Postpaid | LI | SBC05 | ims.mnc060.mcc105.3gppnetwork.org | ims.mnc060.mcc404 | Done | OK
4 | Raj | 9610992567 | 404604770207801 | Vodafone | Postpaid | li | SBC06 | ims.mnc060.mcc106.3gppnetwork.org | ims.mnc060.mcc404
5 | Raj | 9828099251 | 404604770207806 | Vodafone | Postpaid | li | SBC06 | ims.mnc060.mcc106.3gppnetwork.org | ims.mnc060.mcc404
6 | Raj | 9610015250 | 404604770127814 | Vodafone | Postpaid | LI | SBC07 | ims.mnc060.mcc107.3gppnetwork.org | ims.mnc060.mcc404
7 | Raj | 9610015231 | 404604770127811 | Vodafone | Postpaid | IMSI | SBC07 | ims.mnc060.mcc107.3gppnetwork.org | ims.mnc060.mcc404
8 | Raj | 9828183789 | 404604770231150 | Vodafone | Postpaid | LI | SBC08 | ims.mnc060.mcc108.3gppnetwork.org | ims.mnc060.mcc404
9 | Raj | 9828192789 | 404604770231143 | Vodafone | Postpaid | IMSI | SBC08 | ims.mnc060.mcc108.3gppnetwork.org | ims.mnc060.mcc404
10 | Raj | 9828208789 | 404604770231463 | Vodafone | Postpaid | IMSI | SBC06 | ims.mnc060.mcc106.3gppnetwork.org | ims.mnc060.mcc404
11 | Raj | 7733992539 | 404874019805109 | Idea | Postpaid | LI | SBC05 | ims.mnc087.mcc105.3gppnetwork.org | ims.mnc087.mcc404 | Done | OK
12 | Raj | 8058219925 | 404874019805555 | Idea | Postpaid | LI | SBC05 | ims.mnc087.mcc105.3gppnetwork.org | ims.mnc087.mcc404 | NOK | OK
13 | Raj | 9057129254 | 404874019805578 | Idea | Postpaid | LI | SBC05 | ims.mnc087.mcc105.3gppnetwork.org | ims.mnc087.mcc404 |  | OK
14 | Raj | 9694001039 | 404874019805599 | Idea | Postpaid | li | SBC06 | ims.mnc087.mcc106.3gppnetwork.org | ims.mnc087.mcc404
15 | Raj | 9785003592 | 404874019806476 | Idea | Postpaid | li | SBC06 | ims.mnc087.mcc106.3gppnetwork.org | ims.mnc087.mcc404
16 | Raj | 9887010229 | 404874013466133 | Idea | Postpaid | LI | SBC07 | ims.mnc087.mcc107.3gppnetwork.org | ims.mnc087.mcc404
17 | Raj | 7688992596 | 404874019805098 | Idea | Postpaid | IMSI | SBC07 | ims.mnc087.mcc107.3gppnetwork.org | ims.mnc087.mcc404
18 | Raj | 9887120789 | 404874113484909 | Idea | Postpaid | LI | SBC08 | ims.mnc087.mcc108.3gppnetwork.org | ims.mnc087.mcc404
19 | Raj | 9887121789 | 404874113492798 | Idea | Postpaid | IMSI | SBC08 | ims.mnc087.mcc108.3gppnetwork.org | ims.mnc087.mcc404
20 | Raj | 9887129789 | 404874113484639 | Idea | Postpaid | IMSI | SBC06 | ims.mnc087.mcc106.3gppnetwork.org | ims.mnc087.mcc404
21 | Raj | 9983615063 | 404607108365366 | Vodafone | Prepaid |  | SBC05 | ims.mnc060.mcc105.3gppnetwork.org | ims.mnc060.mcc404 |  | OK
22 | Raj | 9983624964 | 404607108365363 | Vodafone | Prepaid |  | SBC05 | ims.mnc060.mcc105.3gppnetwork.org | ims.mnc060.mcc404 |  | OK
23 | Raj | 8094145549 | 404607108365423 | Vodafone | Prepaid | Fan | SBC05 | ims.mnc060.mcc105.3gppnetwork.org | ims.mnc060.mcc404 |  | OK
24 | Raj | 8094146432 | 404607108365424 | Vodafone | Prepaid |  | SBC06 | ims.mnc060.mcc106.3gppnetwork.org | ims.mnc060.mcc404
25 | Raj | 8094146703 | 404607108365429 | Vodafone | Prepaid |  | SBC06 | ims.mnc060.mcc106.3gppnetwork.org | ims.mnc060.mcc404
26 | Raj | 8696822343 | 404604724476215 | Vodafone | Prepaid |  | SBC07 | ims.mnc060.mcc107.3gppnetwork.org | ims.mnc060.mcc404
27 | Raj | 9587328876 | 404607108989547 | Vodafone | Prepaid |  | SBC07 | ims.mnc060.mcc107.3gppnetwork.org | ims.mnc060.mcc404
28 | Raj | 8696033891 | 404607108989546 | Vodafone | Prepaid | FAN | SBC08 | ims.mnc060.mcc108.3gppnetwork.org | ims.mnc060.mcc404
29 | Raj | 9649512198 | 404607108989549 | Vodafone | Prepaid |  | SBC08 | ims.mnc060.mcc108.3gppnetwork.org | ims.mnc060.mcc404
30 | Raj | 9983074357 | 404607108989548 | Vodafone | Prepaid |  | SBC06 | ims.mnc060.mcc106.3gppnetwork.org | ims.mnc060.mcc404
31 | Raj | 9785253524 | 404874012333812 | Idea | Prepaid |  | SBC05 | ims.mnc087.mcc105.3gppnetwork.org | ims.mnc087.mcc404 |  | OK
32 | Raj | 7740998685 | 404874019806997 | Idea | Prepaid |  | SBC05 | ims.mnc087.mcc105.3gppnetwork.org | ims.mnc087.mcc404 |  | OK
33 | Raj | 7740998690 | 404874019807004 | Idea | Prepaid | FAN | SBC05 | ims.mnc087.mcc105.3gppnetwork.org | ims.mnc087.mcc404 |  | OK
34 | Raj | 8058965270 | 404874019807043 | Idea | Prepaid |  | SBC06 | ims.mnc087.mcc106.3gppnetwork.org | ims.mnc087.mcc404
35 | Raj | 8502931450 | 404874019807053 | Idea | Prepaid |  | SBC06 | ims.mnc087.mcc106.3gppnetwork.org | ims.mnc087.mcc404
36 | Raj | 8504064847 | 404874019807054 | Idea | Prepaid | Fan | SBC07 | ims.mnc087.mcc107.3gppnetwork.org | ims.mnc087.mcc404
37 | Raj | 8058239731 | 404874012333800 | Idea | Prepaid |  | SBC07 | ims.mnc087.mcc107.3gppnetwork.org | ims.mnc087.mcc404
38 | Raj | 7240059788 | 404874113480268 | Idea | Prepaid |  | SBC08 | ims.mnc087.mcc108.3gppnetwork.org | ims.mnc087.mcc404
39 | Raj | 7689947661 | 404874113480269 | Idea | Prepaid |  | SBC08 | ims.mnc087.mcc108.3gppnetwork.org | ims.mnc087.mcc404
40 | Raj | 8503923638 | 404874113480272 | Idea | Prepaid |  | SBC06 | ims.mnc087.mcc106.3gppnetwork.org | ims.mnc087.mcc404
404604770207762
404874019805555
9057129254
8503923638-